## Estimate 1
Task | Days | 2010-03-15
List all features in detail | 1 | 2010-03-16
Design the workflow, plug-ins | 1 | 2010-03-17
Discussions over new design | 1 | 2010-03-18
Plug-in split (to be done over the period) | 0 | 2010-03-18
Project setup | 1 | 2010-03-19
fr/resource splitting | 1 | 2010-03-22
Moving code to non-UI. | 2 | 2010-03-24 | 4
Modify gSoap layer interaction to support async calls | 2 | 2010-03-26 | 6
Create utils to support workflow | 3 | 2010-03-31
Modify UI handling of assets list (model) | 2 | 2010-04-02 | 8
InDesign doc (check-in checkout) workflow | 2 | 2010-04-06
Story check-in checkout | 3 | 2010-04-09
InCopy doc (check-in checkout) workflow | 2 | 2010-04-13
Update assets (versioning) | 0 | 2010-04-13
InCopy story | 1 | 2010-04-14
InCopy document | 1 | 2010-04-15
InCopy assignment | 1 | 2010-04-16
InDesign document | 1 | 2010-04-19
Allow DnD of InCopy Document and Link to InDesign doc | 2 | 2010-04-21
Add support for templates | 2 | 2010-04-23
Optimization, profiling | 2 | 2010-04-27
Risk (10%) | 3 | 2010-04-30
Total | 34 | 2010-04-30
Others: | Days
wsdl update took unexpected time | 3

## Estimate 2
Task | Days | 2010-03-15 | Date Passed | Delay
List all features in detail | 1 | 2010-03-16
Design the workflow, plug-ins | 1 | 2010-03-17
Discussions over new design | 1 | 2010-03-18
Plug-in split (to be done over the period) | 0 | 2010-03-18
Project setup | 1 | 2010-03-19
fr/resource splitting | 1 | 2010-03-22
Moving code to non-UI. | 2 | 2010-03-24 |  | 4
Modify gSoap layer interaction to support async calls | 2 | 2010-03-26 |  | 6
Create utils to support workflow | 3 | 2010-03-31
Modify UI handling of assets list (model) | 2 | 2010-04-02 |  | 8
InDesign doc (check-in checkout) workflow | 2 | 2010-05-12 |  | 26
Story check-in checkout | 3 | 2010-05-17
InCopy doc (check-in checkout) workflow | 2 | 2010-05-19
Update assets (versioning) | 0 | 2010-05-19
InCopy story | 1 | 2010-05-20
InCopy document | 1 | 2010-05-21
InCopy assignment | 1 | 2010-05-24
InDesign document | 1 | 2010-05-25
Allow DnD of InCopy Document and Link to InDesign doc | 2 | 2010-05-27
Add support for templates | 2 | 2010-05-31
Optimization, profiling | 2 | 2010-06-02
Risk (10%) | 3 | 2010-06-07
Total | 34 | 2010-04-30
Others: | Days
wsdl update took unexpected time | 3