## Pln Issues
# | Status | Project | Tracker | Priority | NewPriority | Subject | Assigned to | Category | Target version | Author | Start | Due date | % Done | Estimated time | Created | Updated | Description
1383 | Resolved | iZine.UI | Feature | High | 1 | AM: IC document support | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:22 | 2010-08-03 10:22 | Allow new InCopy document to be check-in to our database.
1371 | Resolved | iZine.UI | Feature | Normal | 1 | UI: DnD IC document on ID document | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:58 | 2010-08-03 09:58 | Allow DnD IC document on ID document. Create link after dropping.
1384 | Resolved | iZine.UI | Bug | Low | 2 | Assignment asset should be linked to document asset |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:24 | 2010-08-03 10:24 | When an assignment asset is created, it should be linked with the document in which it is created.
926 | Resolved | iZine.UI | Feature | Normal | 2 | Templates | Rajkumar Sehrawat |  |  | Stefan Ferdinandus | 2010-01-12 |  | 0 |  | 2010-01-12 20:37 | 2010-01-15 12:40 | To use in combination with the edition generator, but not exclusively, templates should be used to create new pages. The designer needs to be able to add and manage the templates.
1397 | Resolved | iZine.UI | Feature | Normal | 2 | InCopy check-in should also ask for check-in comments. |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 15:07 | 2010-08-03 15:07 | Currently the ID story check-in is taking status value from document. It should ask for status value from user. How to change assignment status from InCopy? As InCopy user cannot check-in the assignment file.
1373 | Resolved | iZine.UI | Feature | Normal | 2 | WS: MTOM | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:00 | 2010-08-03 10:00 | MTOM usage during upload files. Download is already using MTOM.
1381 | Resolved | iZine.UI | Bug | Normal | 3 | AM: not able to add mulitple stories to assignment in one go | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:13 | 2010-08-03 10:13 | Select more than one story and add them to assignment. Only one story gets added. No error shown. Expected: All stories must be added.
1425 | Resolved | iZine.UI | Bug | Normal | 3 | Add all stories to assignment is not working |  |  |  | Rakesh Kumar | 2010-08-05 |  | 0 |  | 2010-08-05 13:01 | 2010-08-05 13:01 | In InDesign, selecting the menu item "Edit->InCopy->Add all stories to assignment", a dialog box comes up asking for incx saving path. It should automatically be handled like adding a single story to assignment.
1366 | Resolved | iZine.UI | Bug | Low | 3 | UI: Load values when asset panel is loaded after login | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:55 | 2010-08-03 09:55 | Load values when asset panel is loaded after login
1389 | New | iZine.UI | Feature | High | 3 | AM: Update design menu item not coming in InCopy |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:37 | 2010-08-03 10:37 | When an assignment is modified in InDesign, if that assignment is already open in InCopy, then "Update design" menu item should come on right click in assignment panel for that assignment.
1424 | New | iZine.UI | Feature | High | 3 | UI: Asset name must be set with document/linked story. |  |  |  | Rajkumar Sehrawat | 2010-08-05 |  | 0 |  | 2010-08-05 12:24 | 2010-08-05 12:24 | Asset name set during check-in should be set with document. Linked story name should be taken from story first few chars.
1394 | New | iZine.UI | Feature | High | 4 | UI: Status popup should show ony the assigned status |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 14:42 | 2010-08-03 14:42 | A Title can have different status defined for Layout(InDesign) & Text(InCopy). Popup to select the status during check-in should filter out the status not assigned for the current host application.
1376 | New | iZine.UI | Feature | Low | 4 | AM: cache folder specific for iZine user, not for windows logged in user. |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:04 | 2010-08-03 10:04 | Make cache folder path specific to user logged in. Also the local info needs to be user specific. If other user logs in iZinePublish from the same windows user profile
1390 | Resolved | iZine.UI | Bug | Low | 4 | WS: Not able to upload document of size > 3.7 MB |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:44 | 2010-08-03 10:44 | Gets ssl error message when uploading InDesign document > 3.7 MB. Web Service is not able to take this load.
1370 | Assigned | iZine.UI | Bug | Normal | 4 | UI: Error during login does not reset the login state | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:57 | 2010-08-03 09:57 | Error during login does not reset the login state
1379 | New | iZine.UI | Bug | Normal | 4 | AM: Check-in comments are not being passed to WS |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:06 | 2010-08-03 10:06 | Check-in comments are not being passed to WS. Is Asset Description is same as check-in comment?
1426 | New | iZine.UI | Feature | Normal | 4 | Clear existing db objects cache on logout. |  |  |  | Rajkumar Sehrawat | 2010-08-05 |  | 0 |  | 2010-08-05 13:07 | 2010-08-05 13:07 | After logout clear cached db objects.
1470 | New | iZine.UI | Bug | Normal | 4 | Revertversion |  |  |  | Rakesh Kumar | 2010-08-13 |  | 0 |  | 2010-08-13 15:08 | 2010-08-13 15:08 | In InDesign modify any linked story, and save the document modify the same story again and don't save now revert this document to last revision. After revert the content that was saved is not there. Behavior is correct till this point. Now update assignment, the content that was saved comes up again. First the assignment option should not do anything as assignment was not modified. Second the content that was not check-in should be reverted.
1449 | Resolved | iZine.UI | Bug | Low | 5 | User name is not displaying on assets panel |  |  |  | Rakesh Kumar | 2010-08-05 |  | 0 |  | 2010-08-05 18:35 | 2010-08-05 18:35 | User name is not displaying on assets panel after login. It should be display after login.
1378 | New | iZine.UI | Feature | Low | 5 | UI: Add one more column in Assets panel, for local files state |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:05 | 2010-08-03 10:05 | Add one more column in Assets panel, for local files state, ( modified, conflict, out-of-date, up-to-date )
1386 | New | iZine.UI | Feature | Low | 5 | Local machine cache folder - cleanup |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:31 | 2010-08-03 10:31 | Local machine cache folder should be cleaned. When - Once daily/weekly/monthly. Cleanup should be done only for unmodified assets(saved locally).
1388 | New | iZine.UI | Bug | Low | 5 | Crash: Re-login (login - logout - login another user) |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:34 | 2010-08-03 10:34 | Some time application crashes on Re-login (login - logout - login another user)
1396 | New | iZine.UI | Feature | Low | 5 | UI: assignment panel should show first chars of story |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 15:05 | 2010-08-03 15:05 | For Assigned story, assignment panel should show first( 20-30 ) visible chars as story name Currently incx file name is coming.
1377 | New | iZine.UI | Feature | Normal | 5 | AM: ID template should not have assignments. |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:05 | 2010-08-03 10:05 | Template ID document cannot contain assignments.
1427 | Resolved | iZine.UI | Bug | Low | 6 | The first story being check out automatically |  |  |  | Rakesh Kumar | 2010-08-05 |  | 0 |  | 2010-08-05 15:10 | 2010-08-05 15:10 | Opening assignment file in Incopy, the first story gets check out automatically. It should not check out automatically. That story is check out elsewhere then nothing happens.
1368 | Assigned | iZine.UI | Bug | Low | 6 | UI: Asset list shows less assets | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:57 | 2010-08-03 09:57 | If Asset List is not populated in UI and a new document is check-in then populating the asset list for same edition will show only the new created assets.
1369 | Assigned | iZine.UI | Bug | Low | 6 | UI: Refresh after create/delete/check-in asset. | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:57 | 2010-08-03 09:57 | Refresh after create/delete/check-in asset.
1385 | New | iZine.UI | Feature | Low | 6 | UI: change the lock icon in assets panel |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:27 | 2010-08-03 10:27 | The lock icon ( eye ) should be replaced with similar icon present in links/assignment panel.
1451 | New |  | Feature | Normal | 6 | Handle/Allow assignment/linked story deletion from document |  |  |  | Rajkumar Sehrawat | [6 empty] | Handle assignment/linked story deletion from document or assets panel. Currently if asset is deleted from assets panel, then assignment remains on the document & vice-versa
1458 | New | iZine.UI | Feature | Normal | 6 | UI: Preference - refresh duration | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-16 |  | 0 |  | 2010-08-10 15:06 | 2010-08-10 15:06 | Lock/Version status update duration. Duration after which information will be fetched from server. On Lan it can be 10 seconds and on Internet it should be higher to reduce the network traffic.
1459 | Assigned | iZine.UI | Feature | Normal | 6 | UI: Preference - auto update links. | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-10 |  | 0 |  | 2010-08-10 15:09 | 2010-08-10 15:09 | Update links on opening document. o Meaning if a linked story has become out-of-date, then on opening document it is re-linked automatically. Instead of doing this automatically it should be done on user preference. If enabled then it will automatically update the document with latest version of story otherwise user will have to do that manually by selecting â€œUpdate contentâ€. o By default this preference will be enabled. o This way user will have more control over document updating.
1365 | Assigned | iZine.UI | Bug | Low | 7 | AM: document revert & lock status | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:54 | 2010-08-03 09:54 | After document revert, the lock gets released. To continue working, user have to open it again from asset panel
1036 | New | iZine.UI | Bug | Low | 8 | Refresh button does not refresh dropdowns |  |  |  | Rajkumar Sehrawat | 2010-02-04 |  | 0 |  | 2010-02-04 12:51 | 2010-02-04 12:51 | Assets panel. Refresh button does not refresh the drop downs Title and Edition. When title dropdown is changed then only the Edition list changes.
1364 | New | iZine.UI | Bug | Low | 8 | UI: Login dialog not working when shown during startup | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:53 | 2010-08-03 09:53 | WS idle thread not working when login dialog is opened during startup
1367 | Assigned | iZine.UI | Bug | Low | 8 | UI: Popup/Tree should retain selection during value refresh | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:56 | 2010-08-03 09:56 | Popup/Tree should retain selection during value refresh
1374 | Assigned | iZine.UI | Feature | Low | 8 | Read only document opening. | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:01 | 2010-08-03 10:01 | If lock is not available then document should open as read only.
1380 | New | iZine.UI | Bug | Low | 8 | AM: Save AS â€“ ID/IC/story asset |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:06 | 2010-08-03 10:06 | Save AS â€“ ID/IC/story asset Should we support or disable it? If disabling then disable Save a Copy also.
1382 | New | iZine.UI | Feature | Low | 8 | Handle document recovery |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:16 | 2010-08-03 10:16 | When application is crashed, opening the application again, results in crash again when closing the recovered document.
1372 | New | iZine.UI | Feature | Low | 9 | AM: AM service only for new document or files opened from our replica folder. | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 09:59 | 2010-08-03 09:59 | AM service only for new document or files opened from our replica folder.
54 | Rejected | iZine.UI | Bug | Normal |  | copying exported stories have datalinks copied also |  |  |  | Remco Verhoef | 2009-03-11 |  | 0 |  | 2009-03-12 04:14 | 2009-04-06 19:54
1387 | New | iZine.UI | Bug | Low | 9 | UI: Error message comes fequently if server not available |  |  |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:33 | 2010-08-03 10:33 | If plugin is not able to contact server, and any document is open then error messages comes frequently. Subsequent messages should be suppressed.
61 | Rejected | iZine.UI | Feature | Normal |  | Keep session / authentication with webserver alive in OnIdle | Remco Verhoef |  |  | Remco Verhoef | 2009-03-17 |  | 0 |  | 2009-03-17 17:09 | 2009-05-27 15:34 | Currently the authentication ticket will expire after 8 hours of inactivity. We can do a keepalive in the OnIdle (for every 10 minutes).
1375 | New | iZine.UI | Feature | Low | 10 | Remove Alerts from non-UI plug-in | Rajkumar Sehrawat | DevTask |  | Rajkumar Sehrawat | 2010-08-03 |  | 0 |  | 2010-08-03 10:03 | 2010-08-03 10:03 | Remove Alerts from non-UI plug-in
924 | Feedback | iZine.UI | Bug | Normal |  | Problem with updating design in inCopy during testing | Rajkumar Sehrawat |  |  | Stefan Ferdinandus | 2010-01-12 |  | 0 |  | 2010-01-12 20:16 | 2010-01-19 09:49 | During a test with the latest test plug-in, the users came accross this bug: The following test was done: - User Martijn created a page in inDesign with several assignements - User Linda opened all assignments in inCopy and adds them with text. - Martijn opens the document in inDesign again, checks out all assignments and changes the layout. - Martijn checks in all assignements and saves the indesign document. - Linda opens one of the documents again in inCopy Unfortunately is the new lay out not attached yet, while the preview of the asset pallet displays it correctly. (See image situati1.png) If Martijn opens the document in inCopy on his computer he sees the correct layout displayed in inCopy (see image situatie2.png) Reversing the entire process results in the same, but the other way around, so User Linda sees the correct layout, and Martijn doesn't. Logging in with each others pasword doesn't solve this. It looks like something is save locally?
925 | New | iZine.UI | Feature | Normal |  | Add a Edition Generator | Rajkumar Sehrawat |  |  | Stefan Ferdinandus | 2010-01-12 |  | 0 |  | 2010-01-12 20:32 | 2010-01-15 12:40 | It should be made very easy to generate a new edition for a magazine. The designer should be able to select the number of pages for the new edition and by dragging and dropping he should be able to build an edition very easy. Also see the Feature issue Templates.